## Summary Report
START UP PLAN SUMMARY REPORT | STATUS | NOTES
STATE FILING
State Deadline #1 | 0%
State Deadline #2 | 0%
State Deadline #3 | 0%
State Deadline #4 | 0%
State Deadline #5 | 0%
State Deadline #6 | 0%
State Deadline #7 | 0%
STAFFING
Hire School Leader | 0%
Recruit School Staff | 0%
Select School Staff | 0%
Hire School Staff | 0%
Non Instructional Staff | 0%
STUDENT ENROLLMENT & DATA
Establish SIS | 0%
Establish Onsite Operations | 0%
Recruit Students | 0%
Student / Family Welcome | 0%
Select Students | 0%
Enroll Students | 0%
Schedule Students | 0%
ADMINISTRATIVE
Administrative | 0%
Student Identification | 0%
School Finance | 0%
Parents / Student / Staff | 0%
SHARED SERVICES
Facilities | 0%
General Operations | 0%
Transportation | 0%
Food Service | 0%
Security | 0%
Maintenance | 0%
Custodial | 0%
TECHNOLOGY
Technology Assessment | 0%
Information systems | 0%
Technology procurement | 0%
Website Development | 0%
Erate | 0%
Long-Term Technology Plan | 0%
SIS | 0%
PROCUREMENT
Order and Deliver Materials | 0%
PROFESSIONAL DEVELOPMENT
Logistics | 0%
FACILITIES
Facilities | 0%
Construction | 0%
CLIMATE
Classrooms / Specialty Rooms | 0%
School Climate and Safety | 0%
SPECIALIZED SERVICES
Food Service | 0%
Special Education | 0%
School Nurse | 0%
HUMAN RESOURCES
HR Office Compliance and Setup | 0%
Hiring process and setup for new hires | 0%
Employment Manual | 0%
Benefits, payroll and insurance | 0%
Recruiting process for HR administrator | 0%
New Hire Orientation Process | 0%
Termination Policies and Policies | 0%
FINANCE
Accounting | 0%
Revenue | 0%
Payroll | 0%
Purchasing | 0%
Accounts Payable | 0%
Inventory - Fixed Assets Mgmt | 0%
Employee Reimbursements | 0%
Reporting | 0%
Budget Management | 0%
Petty Cash | 0%
Insurance | 0%
Other Potential Things | 0%
GRANTS
Grants | 0%
Parents / Students | 0%
Competitive Applications | 0%

## Staffing
TASKS & STEPS | Team Member(s): | Target Completion Date | School #1 Project Status | School #2 Project Status | Evidence of Status | NOTES | Final Completion Date
HIRE SCHOOL LEADER |  |  | Completion (0 = not started, 10 = Complete) | Completion (0 = not started, 10 = Complete)
Draft advertisement for Principal |  |  | 0 | 0
Approve advertisement |  |  | 0 | 0
Run advertisement in local newspaper and area career placement newsletters. |  |  | 0 | 0
Make “networking” contacts to recruit candidates for principal and create diverse field |  |  | 0 | 0
Receive and organize letters of interest and resumes |  |  | 0 | 0
Organize selection committee |  |  | 0 | 0
Review applications and select candidates for interview based on weighted Level |  |  | 0 | 0
Evaluate applicant pool for diversity |  |  | 0 | 0
Schedule interviews |  |  | 0 | 0
Conduct interviews for Principal with Selection Committee |  |  | 0 | 0
Identify finalist and check references |  |  | 0 | 0
Schedule site visits |  |  | 0 | 0
Align compensation with budget |  |  | 0 | 0
Recommend Principal for approval |  |  | 0 | 0
Hire Principal |  |  | 0 | 0
RECRUIT SCHOOL STAFF
Draft advertisement for staff |  |  | 0 | 0
Approve advertisement |  |  | 0 | 0
Run advertisement in Local and National newspaper and area career placement newsletters |  | Continuous | 0 | 0
Make “networking” contacts to recruit candidates to create diverse field |  | Continuous | 0 | 0
Receive and organize letters of interest and resumes |  | Continuous | 0 | 0
SELECT SCHOOL STAFF
Number of vacancies identified and filled |  | Continuous | 0 | 0
School staffing issues identified and communicated to Human Resources |  | Continuous | 0 | 0
Review applicant pool for diversity |  | Continuous | 0 | 0
Review letters of interest, applications, and resumes and select candidates for all interviews |  | Continuous | 0 | 0
Schedule candidates interview |  | Continuous | 0 | 0
Attend Human Resources site selection and placement activities for teacher vacancies |  | Continuous | 0 | 0
HIRE SCHOOL STAFF
Align compensation with budget |  | Continuous | 0 | 0
Conduct finalist interviews ; |  |  | 0 | 0
Check references, |  |  | 0 | 0
Get principal approval; if possible |  |  | 0 | 0
Hire Staff |  |  | 0 | 0
All teacher staff positions filled: |  |  | 0 | 0
Grades |  |  | 0 | 0
Library |  |  | 0 | 0
Athletics |  |  | 0 | 0
New staff orientations scheduled and convened |  |  | 0 | 0
Buddy teachers assigned |  |  | 0 | 0
Principal meet with all new or departing staff and review assignments with them / transition plan |  |  | 0 | 0
NON INSTRUCTIONAL STAFF
All non-instructional staff positions filled: |  |  | 0 | 0
Secretaries identified |  |  | 0 | 0
Para Professionals |  |  | 0 | 0
non-Instructional Managers |  |  | 0 | 0
Non instructional staff assigned and deployed - i.e. Paraprofessionals and Parent liaisons |  |  | 0 | 0

## Student Enrollment & Data
TASKS & STEPS | Team Member(s): | Target Date | School #1 Project Status | School #2 Project Status | Evidence of Status | NOTES | Final Completion Date
ESTABLISH SIS |  |  | Completion (0 = not started, 10 = Complete) | Completion (0 = not started, 10 = Complete)
Schedule Demo with JPAMS, Panamation, and Power Schools |  |  | 0 | 0
Determine SIS Software |  |  | 0 | 0
Determine training needs on SIS software |  |  | 0 | 0
Set up SIS |  |  | 0 | 0
ESTABLISH ONSITE OPERATIONS
Establish onsite startup office |  |  | 0 | 0
Identify office support staff |  |  | 0 | 0
Set up technology for onsite data management |  |  | 0 | 0
Provide training to office support staff, as needed |  |  | 0 | 0
RECRUIT STUDENTS
Prepare mailing to announce enrollment process to parents |  |  | 0 | 0
Identify community liaisons |  |  | 0 | 0
Solicit and organize parent support |  | Continuous | 0 | 0
Customize your student applications (specific to school, year, etc.) |  |  | 0 | 0
Duplicate and distribute applications |  |  | 0 | 0
Provide materials for community presentations |  |  | 0 | 0
Conduct community presentations; |  | Continuous | 0 | 0
Monitor applications for number, compliance with diversity goals |  | Continuous | 0 | 0
Student / Family Welcome
Begin enrolling students |  |  | 0 | 0
Identify parent and community volunteers to plan orientation and welcoming events |  |  | 0 | 0
Recruit parent volunteers |  |  | 0 | 0
Organize meetings to introduce parents to house teachers and teacher assignments |  |  | 0 | 0
Conduct meetings to introduce parents to house teachers and teacher assignments |  |  | 0 | 0
Explain special programs and school's approach to special needs students |  |  | 0 | 0
Conduct welcoming/orientation events |  |  | 0 | 0
Plan opening day activities, including locations and dates |  |  | 0 | 0
Inform parents/students of orientation and welcoming events by mail |  |  | 0 | 0
SELECT STUDENTS
Conduct Student Lottery if necessary |  |  | 0 | 0
Establish list of selected students |  |  | 0 | 0
Establish waiting list |  |  | 0 | 0
Establish waiting list for Pre-K |  |  | 0 | 0
Send letters inviting selected students to enroll |  |  | 0 | 0
Send letters informing other applicants of waiting list status |  |  | 0 | 0
Send letters inviting wait listed students to enroll in event of open spot |  |  | 0 | 0
Inform Parents of selected Pre-K students |  |  | 0 | 0
Send letters informing other applicants of wait list status for Pre-K |  |  | 0 | 0
Continue monitoring of Student enrollment until count day |  | Continuous | 0 | 0
ENROLL STUDENTS
Begin Enrollment process |  |  | 0 | 0
Set up student information system |  |  | 0 | 0
Review IEP requirements of special needs students; determine placement requirements |  |  | 0 | 0
Prepare final reports for Count Day |  |  | 0 | 0
Count Day |  |  | 0 | 0
Closeout Count Day activities |  |  | 0 | 0
SCHEDULE STUDENT
Feasibility Analysis of school (coordinate with facilities) |  |  | 0 | 0
Produce draft school schedule |  |  | 0 | 0
School leadership team reviews schedule (Principal/Leadership) |  |  | 0 | 0
Review implications of schedule (Facility, Budget, Staffing Materials, Training) |  |  | 0 | 0
Align schedule implications to budget |  |  | 0 | 0
Add Leadership Team Training to school schedule |  |  | 0 | 0
Add Staff Training to school schedule |  |  | 0 | 0
School schedule approval |  |  | 0 | 0

## Administrative
TASKS & STEPS | Team Member(s): | Target Date | School #1 Project Status | School #2 Project Status | Evidence of Status | Notes | Final Completion Date
ADMINISTRATIVE |  |  | Completion (0 = not started, 10 = Complete) | Completion (0 = not started, 10 = Complete)
Registration procedures and staff in place to execute |  |  | 0 | 0
Staff handbook distributed and reviewed with staff |  |  | 0 | 0
Email accounts for school staff are operational |  |  | 0 | 0
Rosters and school schedules prepared for distribution to students |  |  | 0 | 0
Plans in place to assign missing students rosters and schedules |  |  | 0 | 0
School Improvement and School Progress Plans ready for distribution (staff/office) |  |  | 0 | 0
Teachers' weekly and emergency lesson plans on file |  |  | 0 | 0
Teacher guidelines and staff meeting agendas/professional development dates prepared |  |  | 0 | 0
School trip information distributed to staff |  |  | 0 | 0
Schedule for parent night |  |  | 0 | 0
New Teacher Orientations - scheduled and new teachers notified |  |  | 0 | 0
Mentor or buddy teacher for new teachers trained and assigned |  |  | 0 | 0
Professional Development materials ready for all staff |  |  | 0 | 0
Faculty meeting and professional development dates distributed |  |  | 0 | 0
Testing schedule disseminated to teachers |  |  | 0 | 0
Staff attendance memos prepared |  |  | 0 | 0
Grade Team Meetings Formed |  |  | 0 | 0
School guidelines ready for distribution in written form - i.e. school calendar, student handbook, etc. |  |  | 0 | 0
Ensure school has and efficient ehrollment/transfer/withdrawal process |  |  | 0 | 0
Student records received |  |  | 0 | 0
Roll sheets received |  |  | 0 | 0
Summer program promotion/retention data reviewed |  |  | 0 | 0
All professional development agendas, sign-in sheets are in a binder clearly labeled by grant or activity. |  |  | 0 | 0
Kindergarten Screening |  |  | 0 | 0
STUDENT IDENTIFICATION
School holds orinetation and takes ID pictures |  |  | 0 | 0
Student ID equipment obtained |  |  | 0 | 0
Student ID equipment/training completed |  |  | 0 | 0
Pictures taken of new students and ID cards created |  |  | 0 | 0
Student ID's distributed |  |  | 0 | 0
SCHOOL FINANCE
Payroll secretary had been trained and has password codes to input staff attendance |  |  | 0 | 0
Principal reviews and is familiar with all financial policies for 2009-10 |  |  | 0 | 0
Petty Case/Student Actiivty Fund bank account signatures updated |  |  | 0 | 0
All Budgets Loaded |  |  | 0 | 0
Personal Property Inventory Review |  |  | 0 | 0
Access ISIS-HR and Payroll Systems and ISIS Web-reports |  |  | 0 | 0
Risk Management and Workers Compensation: a) Workers Compensation Policy; b) Distribute Voluntary Student Accident Brochure to all students to be taken home to parent/guardian |  |  | 0 | 0
PARENTS/STUDENTS/STAFF
School guidelines ready for dsitribution |  |  | 0 | 0
Calendar |  |  | 0 | 0
Student Handbook |  |  | 0 | 0
Report card Dates |  |  | 0 | 0
Uniform Policy |  |  | 0 | 0
Rosters |  |  | 0 | 0
Student Code of Conduct |  |  | 0 | 0
Parent Resource Center established |  |  | 0 | 0
Kindergarten parent surveys have been distributed to Kindergarten teachers |  |  | 0 | 0

## Shared Services
TASKS & STEPS | Team Member(s): | Target Date | School #1 Project Status | School #2 Project Status | Evidence of Status | NOTES | Final Completion Date
FACILITIES |  |  | Completion (0 = not started, 10 = Complete) | Completion (0 = not started, 10 = Complete)
Obtain access to the facilities |  |  | 0 | 0
Complete MOU with district |  |  | 0 | 0
Establish utility accounts: Electric, Fuel, Telephone |  |  | 0 | 0
Finalize agreement with district for facility access |  |  | 0 | 0
GENERAL OPERATIONS
Schedule meeting with district to determine structure |  |  | 0 | 0
Define general operations requirements |  |  | 0 | 0
Custodial (Grounds upkeep, Trash removal, etc.) |  |  | 0 | 0
Facility Maintenance (Pest Control, HVAC, etc.) |  |  | 0 | 0
Security |  |  | 0 | 0
Transportation |  |  | 0 | 0
Food Service |  |  | 0 | 0
Establish operations strategy (i.e. self-perform, district buy back, sub contract) |  |  | 0 | 0
TRANSPORTATION
Finalize general transportation plan contract |  |  | 0 | 0
Finalize bus contract for SPED |  |  | 0 | 0
Establish bus routes based on enrollment data |  |  | 0 | 0
Notify parents of bus routes/times |  |  | 0 | 0
Trial runs for bus service |  |  | 0 | 0
Launch bus service |  |  | 0 | 0
FOOD SERVICE
Finalize food service contract |  |  | 0 | 0
Make any modifications necessary to provide food service (staffing, POS system, etc.) |  |  | 0 | 0
File necessary paperwork for Free and Reduced lunch |  |  | 0 | 0
Secure food and other materials to prepare meals |  |  | 0 | 0
Conduct staff training |  |  | 0 | 0
Launch food service |  |  | 0 | 0
SECURITY
Evaluate existing alarm system (Transfer codes and system from district) |  |  | 0 | 0
Determine if new alarm system is needed |  |  | 0 | 0
If new, secure new vendor and contract |  |  | 0 | 0
If new, install new system |  |  | 0 | 0
If new, test system and confirm operation |  |  | 0 | 0
If existing , transfer codes and system from district |  |  | 0 | 0
Finalize alarm system transfer and/or confirm functionality |  |  | 0 | 0
MAINTENANCE
Conduct facility assessment to determine short and long-term facility needs |  |  | 0 | 0
Communicate long-term facility needs to district |  |  | 0 | 0
Develop action plan for immediate/urgent short term needs |  |  | 0 | 0
Finalize ongoing maintenance contract or shared service buyback |  |  | 0 | 0
Negotiate with district to resolve any immediate capital needs |  |  | 0 | 0
Contract with service providers to resolve any immediate non-capital needs |  |  | 0 | 0
Complete immediate non-capital needs |  |  | 0 | 0
CUSTODIAL
Produce RFP for Custodial contract |  |  | 0 | 0
Finalize custodial contract |  |  | 0 | 0
If self-performing: conduct interviewing, hiring, on-boarding, training process |  |  | 0 | 0
If outsourcing - finalize detailed work scope |  |  | 0 | 0
Finalize any ancillary contracts (trash removal, etc.) |  |  | 0 | 0

## Tech
TASKS & STEPS | Team Member(s): | Target Date | School #1 Project Status | School #2 Project Status | Evidence of Status | NOTES | Final Completion Date
TECHNOLOGY ASSESSMENT |  |  | Completion (0 = not started, 10 = Complete) | Completion (0 = not started, 10 = Complete)
Review current technology, hardware and software for use by school |  |  | 0 | 0
Conduct technology inventory |  |  | 0 | 0
INFORMATION SYSTEMS
Finalize Student Information System (SIS) |  |  | 0 | 0
Finalize Financial Information Systems |  |  | 0 | 0
Align HR Information System with Payroll, Finance, etc. |  |  | 0 | 0
Finalize network/hardware/server plan |  |  | 0 | 0
Order equipment |  |  | 0 | 0
Install equipment and set up network |  |  | 0 | 0
TECHNOLOGY PROCUREMENT (HIGH VOLUME ORDER - IF NECESSARY)
Determine AV and phone system in conjunction with facility assessment |  |  | 0 | 0
Determine quantity and type of computer equipment |  |  | 0 | 0
Provide a distribution list, indicating where equipment should be stored and installed |  |  | 0 | 0
Turn over system for tracking inventory to site-based operations managers |  |  | 0 | 0
Receive equipment and distribute |  |  | 0 | 0
WEBSITE DEVELOPMENT
Identify web designer |  |  | 0 | 0
Determine basic website content |  |  | 0 | 0
Launch website |  |  | 0 | 0
E-RATE
Finalize e-rate application manager |  |  | 0 | 0
Submit initial e-rate application |  |  | 0 | 0
Manage ongoing e-rate application process |  |  | 0 | 0
LONG TERM TECHNOLOGY PLAN
Prepare initial draft, aligned with school goals and resources |  |  | 0 | 0
Review plan and provide feedback |  |  | 0 | 0
Finalize full 3 year plan |  |  | 0 | 0
Student Information System (SIS)
Set up technology for onsite data management |  |  | 0 | 0
Review serious incident procedures involving SIS |  |  | 0 | 0
Schedule incoming students |  |  | 0 | 0
Assign students homeroom / advisories |  |  | 0 | 0

## Procurement
TASKS & STEPS | Team Member(s): | Target Date | School #1 Project Status | School #2 Project Status | Evidence of Status | NOTES | Final Completion Date
ORDER/DELIVER MATERIALS |  |  | Completion (0 = not started, 10 = Complete) | Completion (0 = not started, 10 = Complete)
Identify core materials that need to be ordered including any furniture materials |  |  | 0 | 0
FURNITURE |  |  | 0 | 0
CURRICULUM |  |  | 0 | 0
SERVICES |  |  | 0 | 0
Create written inventory showing what materials will be used from site inventory |  |  | 0 | 0
Arrange for placement of orders for required books, materials, and furniture |  |  | 0 | 0
Determine projected delivery dates for texts and materials |  |  | 0 | 0
Identify texts and materials that are on backorder. Make alternate arrangements, if possible |  |  | 0 | 0
Apprise Principal and SOM of materials delivery plans, including inventory and schedule |  |  | 0 | 0
Plan for delivery of materials to the school site- determine where/when space will be available for delivery |  |  | 0 | 0
Establish system for tracking delivery of materials to site and how materials will be distributed to classrooms |  |  | 0 | 0
Confirm delivery of instructional materials on site |  |  | 0 | 0
Textbooks ready and inventoried for classroom and student use |  |  | 0 | 0
Teacher guides ready and in place for teacher use |  |  | 0 | 0
Textbook policy distributed to staff and students |  |  | 0 | 0

## Professional Development
TASKS & STEPS | Team Member(s): | Target Date | School #1 Project Status | School #2 Project Status | Evidence of Status | NOTES | Final Completion Date
PROFESSIONAL DEVELOPMENT/PROVIDE OPEN YEAR TRAINING |  |  | Completion (0 = not started, 10 = Complete) | Completion (0 = not started, 10 = Complete)
Determine topics to be covered, experts for start-up professional development and on-going support |  |  | 0 | 0
Identify site for start-up professional development |  |  | 0 | 0
Arrange for materials, equipment for programs |  |  | 0 | 0
Develop schedule for pre-opening professional development programs using regional training cohort |  |  | 0 | 0
Communicate schedule and plan for professional development to staff |  |  | 0 | 0
Identify materials and equipment needed for professional development |  |  | 0 | 0
Conduct professional development seminars |  |  | 0 | 0
Arrange for ongoing professional development |  |  | 0 | 0
Develop Master Calendar to determine dates for ongoing PD |  |  | 0 | 0

## Facilities
TASKS & STEPS | Team Member(s): | Target Date | School #1 Project Status | School #2 Project Status | Evidence of Status | NOTES | Final Completion Date
Facilities |  |  | Completion (0 = not started, 10 = Complete) | Completion (0 = not started, 10 = Complete)
Ensure all bells and alarms are working and clocks set |  |  | 0 | 0
Facility work orders submitted with follow-up dates |  |  | 0 | 0
Pest control addressed |  |  | 0 | 0
Dumpsters located in appropriate location for waste disposal and pick-up |  |  | 0 | 0
Lavatories inspected for operation, cleanliness and supplies |  |  | 0 | 0
Lunchroom inspected for cleanliness and ability for food preparation |  |  | 0 | 0
Graffiti removed from interior and exterior walls |  |  | 0 | 0
Classrooms cleaned, repairs made/scheduled, painting complete |  |  | 0 | 0
Locks in working order |  |  | 0 | 0
Exterior doors/locks/panic bolts in working order |  |  | 0 | 0
All doors clear of debris |  |  | 0 | 0
Grounds needs addressed: lawn, bushes, trash, broken equipment, dumpsters located in safe area away from children |  |  | 0 | 0
Speaker/ Phone System: check for operation maintain list of contacts for assistance |  |  | 0 | 0
CONSTRUCTION
Contractor work schedules reviewed |  |  | 0 | 0
Boiler, emergency generator, and/or window replacements |  |  | 0 | 0
New construction projects begun/ completed |  |  | 0 | 0
Fire Alarm assessed |  |  | 0 | 0
Fire Inspection complete |  |  | 0 | 0
Signage ordered from BR Police Supply |  |  | 0 | 0
Signs posted around facility |  |  | 0 | 0
MAINTENANCE
Conduct facility assessment to determine short and long-term facility needs |  |  | 0 | 0
Communicate long-term facility needs to Board |  |  | 0 | 0
Develop action plan for immediate/urgent short term needs |  |  | 0 | 0
Finalize ongoing maintenance contract or shared service buyback |  |  | 0 | 0
Negotiate with Lesee to resolve any immediate capital needs |  |  | 0 | 0
Contract with service providers to resolve any immediate non-capital needs |  |  | 0 | 0
Complete immediate non-capital needs |  |  | 0 | 0

## Climate
TASKS & STEPS | Team Member(s): | Target Date | School #1 Project Status | School #2 Project Status | Evidence of Status | NOTES | Final Completion Date
CLASSROOMS/SPECIALTY ROOMS |  |  | Completion (0 = not started, 10 = Complete) | Completion (0 = not started, 10 = Complete)
Classroom and school-wide behavior and safety rules posted |  |  | 0 | 0
Classroom prepared-academic (Bulletin board, learning areas, etc.) |  |  | 0 | 0
Classroom prepared - facilities (lights, shades, furniture, etc.) |  |  | 0 | 0
All teachers have classroom keys |  |  | 0 | 0
Classroom keys are inventoried and stored securely |  |  | 0 | 0
All classrooms with new teachers have adequate and appropriate materials, supplies and equipment |  |  | 0 | 0
Supplies received and placed in rooms (markers, pencils, paper, etc.) |  |  | 0 | 0
Computer/science labs operational: ALL borrowed equipment returned |  |  | 0 | 0
Library staffed and ready to open |  |  | 0 | 0
Gym equipped and fields ready for use |  |  | 0 | 0
Teacher classroom assignments completed |  |  | 0 | 0
All new students have been entered in JPAMS/e School (Including Pre K and K) |  |  | 0 | 0
Roll Sheets and instructions shared with staff |  |  | 0 | 0
SCHOOL CLIMATE AND SAFETY
School security needs identified |  |  | 0 | 0
Security equipment assessed |  |  | 0 | 0
Documentation of fire drills |  |  | 0 | 0
School Safety Plans submitted |  |  | 0 | 0
Alarm pads and codes working |  |  | 0 | 0
Security cameras and monitors operations (internal and external) |  |  | 0 | 0
High Schools: Metal Detectors, scanners, wands operational |  |  | 0 | 0
School Deployment Plan Updated |  |  | 0 | 0
Student Code of Conduct distributed and available |  |  | 0 | 0
Sufficient visitor passes available, visitor procedures posted on entrance doors |  |  | 0 | 0
Establish schedule for monthly meetings with behavioral health and student support service providers |  |  | 0 | 0
Ensure the school-wide behavioral expectations are established and clearly posted across classroom and non-classroom settings |  |  | 0 | 0
Establish a plan for student instruction on behavioral expectations |  |  | 0 | 0
Establish a system of positive reinforcement for appropriate behavior |  |  | 0 | 0
Establish a plan for a systematic, structured approach to managing transitions (lunch, recess, dismissal) |  |  | 0 | 0
Crossing Guard needs/assignments |  |  | 0 | 0
Shelter in place and drills scheduled |  |  | 0 | 0
School safety point person identifed and safety team members identified an posted in Main Office |  |  | 0 | 0
Entrance/dismissal procedures disseminated to staff and students |  |  | 0 | 0
Emergency Response Charts completed and posted in all classrooms and offices |  |  | 0 | 0
Duty schedule established (teachers assigned to specific locations across campus) and given to all staff |  |  | 0 | 0

## Specialized Services
TASKS & STEPS | Team Member(s): | Target Date | School #1 Project Status | School #2 Project Status | Evidence of Status | NOTES | Final Completion Date
FOOD SERVICE |  |  | Completion (0 = not started, 10 = Complete) | Completion (0 = not started, 10 = Complete)
Free and reduced lunch applications reach school |  |  | 0 | 0
Free and reduced lunch applications distributed to parents/students |  |  | 0 | 0
Information on breakfast serving times to parents |  |  | 0 | 0
Breakfast/Lunchroom procedures (supervising students) |  |  | 0 | 0
SPECIAL EDUCATION
Identify students whose applications indicate IEPs |  |  | 0 | 0
Identify students whose applications indicate bilingual or ESOL services |  |  | 0 | 0
Gather and review IEPs for special education students (request from former district) |  |  | 0 | 0
Gather and review language skill level on bilingual or ESOL students |  |  | 0 | 0
Devise plans for serving special education students |  |  | 0 | 0
Devise plans for serving bilingual and ESOL students |  |  | 0 | 0
Confer with principal regarding staffing, scheduling, and budgeting implications for special education |  |  | 0 | 0
Confer with principal regarding staffing, scheduling, and budgeting implications for bilingual and ESOL programs |  |  | 0 | 0
Advise special education staff of special education plan |  |  | 0 | 0
Advise bilingual and ESOL staff of bilingual and ESOL program plans |  |  | 0 | 0
Convey special education plans to special education and regular education staff |  |  | 0 | 0
Convey bilingual and ESOL program plans to bilingual, ESOL, and regular education staff |  |  | 0 | 0
Coordinate schedule for special education students |  |  | 0 | 0
Coordinate schedule for bilingual and ESOL students |  |  | 0 | 0
Work with parents to develop or revise IEPs as needed |  |  | 0 | 0
Work with parents to develop or revise bilingual and ESOL programs as needed |  |  | 0 | 0
Ensure the appropriate staff have passwords to access SER |  |  | 0 | 0
Ensure that SER data for students receiving special education services is accurate |  |  | 0 | 0
Student IEPs are stored appropriately with folder holder |  |  | 0 | 0
Students' accommodation pages are disseminated to all teachers |  |  | 0 | 0
SCHOOL NURSES
Determine if Nurse is shared service or District Employee |  |  | 0 | 0
Hire School Nurse (If employee) |  |  | 0 | 0
Negotiate services with district (if shared) |  |  | 0 | 0
School nurse schedule developed and adequate health supplies available |  |  | 0 | 0
School nurse reviewed student health plans for students who should be placed on medical alert list. |  |  | 0 | 0

## Human Resources
TASKS & STEPS | Team Member(s): | Target Date | School #1 Project Status | School #2 Project Status | Evidence of Status | NOTES | Final Completion Date
HR Office Compliance and Set-up |  |  | Completion (0 = not started, 10 = Complete) | Completion (0 = not started, 10 = Complete)
Compliance set-up | HR |  | 0 | 0
Post required state and Federal posters | HR |  | 0 | 0
Set-up employee personnel files | HR | Continuous | 0 | 0
Ensure I-9s and hire register are completed properly | HR | Continuous | 0 | 0
Determine file management process | HR |  | 0 | 0
Ensure compliance with key employment regulations based on employer's size (FLSA, FMLA, COBRA, ADA, OSHA, etc.) | HR |  | 0 | 0
HR Online setup | HR |  | 0 | 0
Prepare a complete and accurate list of key HR contacts at the client including benefits and payroll | HR |  | 0 | 0
Hiring Process and Set-up for New Hires
Determine new hire process | HR |  | 0 | 0
Prepare offer letter template | HR |  | 0 | 0
Prepare reference checklist | HR |  | 0 | 0
Prepare application | HR |  | 0 | 0
Collect all new hire paperwork | HR | Continuous | 0 | 0
Employment Manual
Review and finalize Manual | HR |  | 0 | 0
Implement required updates | HR |  | 0 | 0
Employee information receipt/acknowledgement form | HR |  | 0 | 0
Benefits, Payroll and Insurance Set-up
Determine broker to work with on benefit plans | HR |  | 0 | 0
Determine broker to work with on 403b plans | HR |  | 0 | 0
Determine and implement employee benefits package | HR |  | 0 | 0
Determine 4013b and implement | HR |  | 0 | 0
Determine Flexible Spending vendor and implement | HR |  | 0 | 0
Develop benefits summary | HR |  | 0 | 0
Set-up Workers' Compensation | HR |  | 0 | 0
Set-up Employment Practices Liability insurance | HR |  | 0 | 0
Set-up Unemployment Compensation Insurance | HR |  | 0 | 0
Set-up Payroll vendor | HR |  | 0 | 0
Set-up Payroll cycle | HR |  | 0 | 0
Recruiting Process for HR Administrator
Develop job description | HR |  | 0 | 0
Recruit and hire HR administrator | HR |  | 0 | 0
Transfer ownership to HR Administrator | HR |  | 0 | 0
New Hire Orientation Process Development
Offer letters prepared and provided to all staff | HR |  | 0 | 0
Employment Agreements provided to new hires | HR |  | 0 | 0
Provide all new employees with new hire paperwork and in-process | HR |  | 0 | 0
Determine pre-employment testing and background check procedures | HR |  | 0 | 0
On-Board new employees-benefits overview and processing and school policy review | HR |  | 0 | 0
New Hire checklist | HR |  | 0 | 0
Termination Policies and Procedures
Termination policies | HR |  | 0 | 0
Documentation of specific situations | HR |  | 0 | 0
Termination checklist | HR |  | 0 | 0
Employee release form | HR |  | 0 | 0
COBRA or benefits continuation material | HR |  | 0 | 0
Company return policy | HR |  | 0 | 0

## Finance Detail
TASKS & STEPS | Category | Team Member's): | Team Member's): | Priority Level | Target Date | School #1 Project Status | School #2 Project Status | Evidence of Status | NOTES | Final Completion Date
Accounting |  | Lead | Secondary(s) | (1 must have, 10 save for last) |  | Completion (0 = not started, 10 = Complete) | Completion (0 = not started, 10 = Complete)
Chart of Accounts - All accounts | Finance |  |  | 1 |  | 0 | 0
Chart of Accounts with full descriptions - All accounts | Finance |  |  | 4 |  | 0 | 0
Grant chart and baseline descriptions | Finance |  |  | 4 |  | 0 | 0
Setup of accounts within accounting system | Finance |  |  | 3 |  | 0 | 0
Closing calendar | Finance |  |  | 3 |  | 0 | 0
Revenue & A/R template design | Finance |  |  | 3 |  | 0 | 0
Revenue & A/R procedure | Finance |  |  | 4 |  | 0 | 0
Payroll Accounting template - design | Finance |  |  | 2 |  | 0 | 0
Payroll reconciliation design | Finance |  |  | 3 |  | 0 | 0
Adjust model to generate summer pay accrual figures | Finance |  |  | 1 |  | 0 | 0
Calculate monthly summer pay entry | Finance |  |  | 3 |  | 0 | 0
Standardize sum pay quarterly adjust process | Finance |  |  | 5 |  | 0 | 0
Calculate monthly bonus entry | Finance |  |  | 3 |  | 0 | 0
Standardize bonus quarterly adjust process | Finance |  |  | 5 |  | 0 | 0
Grants accounting design | Finance |  |  | 3 |  | 0 | 0
Grants accounting add names | Finance |  |  | 5 |  | 0 | 0
Payroll accounting process | Finance |  |  | 5 |  | 0 | 0
Generic accounting entry template | Finance |  |  | 2 |  | 0 | 0
General accounting entry process | Finance |  |  | 5 |  | 0 | 0
Policies & procedures write-up | Finance |  |  | 3 |  | 0 | 0
Bank reconciliation protocol | Finance |  |  | 4 |  | 0 | 0
Activity fund reconciliation protocol | Finance |  |  | 5 |  | 0 | 0
Revenue
Initial consolidated grant application | Finance |  |  | 2 |  | 0 | 0
Initial consolidated grant budget | Finance |  |  | 2 |  | 0 | 0
School Improvement Budget | Finance |  |  | 2 |  | 0 | 0
PCSP Budget | Finance |  |  | 2 |  | 0 | 0
Grants available research on process | Finance |  |  | 4 |  | 0 | 0
Grant drawdown research on forms and timing | Finance |  |  | 4 |  | 0 | 0
Grants reporting process | Finance |  |  | 5 |  | 0 | 0
Fundraising process (tracking money coming in, tracking restrictions, thank you / tax letters, contact with donors) | Fundraising |  |  | 5 |  | 0 | 0
Calendar of revenue deadlines, including grants and foundation restrictions | Finance |  |  | 3 |  | 0 | 0
Payroll
Paychex setup | Finance |  |  | 1 |  | 0 | 0
HR Online setup | Finance |  |  | 3 |  | 0 | 0
Development of payroll calendar/deadlines | Finance |  |  | 2 |  | 0 | 0
Updating of timesheet requirements & timesheets | Finance |  |  | 2 |  | 0 | 0
Payroll processing procedures (include how things will be prorated) | Finance |  |  | 3 |  | 0 | 0
Communication of payroll processes to managers and staff (initial and ongoing) | Finance |  |  | 3 |  | 0 | 0
Payroll approval spreadsheet | Finance |  |  | 2 |  | 0 | 0
Late hire calculator | Finance |  |  | 3 |  | 0 | 0
Vacation day tracking system | HR/Finance |  |  | 4 |  | 0 | 0
Sick Day tracking system | HR/Finance |  |  | 4 |  | 0 | 0
Substitute pay policy | HR/Finance |  |  | 3 |  | 0 | 0
Substitute tracking system vs. employee | HR/Finance |  |  | 4 |  | 0 | 0
TAT pay/benefit policy | HR/Finance |  |  | 3 |  | 0 | 0
Stipend forms | HR/Finance |  |  | 4 |  | 0 | 0
Payroll document retention policies | Finance |  |  | 4 |  | 0 | 0
TRSL Adds spreadsheet | Finance |  |  | 3 |  | 0 | 0
TRSL Monthly contributions spreadsheet | Finance |  |  | 3 |  | 0 | 0
TRSL Monthly process | Finance |  |  | 4 |  | 0 | 0
TRSL terminations process | HR/Finance |  |  | 4 |  | 0 | 0
TRSL Eligibility guidelines | HR/Finance |  |  | 2 |  | 0 | 0
TRSL process of determining which plan | HR/Finance |  |  | 3 |  | 0 | 0
Purchasing
Revisit approval requirements (recurring vs. non-recurring) | Finance |  |  | 3 |  | 0 | 0
Bidding/quote requirements (thresholds and documentation) | Operations |  |  | 3 |  | 0 | 0
Research potential purchasing systems (ex: Eschoolmall) | Operations |  |  | 4 |  | 0 | 0
New vendor documentation packet | Finance |  |  | 3 |  | 0 | 0
Change of billing address | Operations |  |  | 3 |  | 0 | 0
Identifying core vendors based on location, price and delivery, etc (classroom supplies, paper, emergency supplies, textbook/workbook companies, assessments, basic repairs, copier repairs, food delivery, printing company | Operations / Finance |  |  | 4 |  | 0 | 0
Setting up accounts with core vendors | Finance |  |  | 3 |  | 0 | 0
Alcohol policies | Operations |  |  | 4 |  | 0 | 0
Apply for state tax exemption | Finance |  |  | 1 |  | 0 | 0
Inform vendors of tax exemption | Finance |  |  | 3 |  | 0 | 0
Receiving/returns process | Operations / Finance |  |  | 4 |  | 0 | 0
Write-up of official purchasing process | Operations / Finance |  |  | 4 |  | o | o
Accounts Payable
Revisit approval requirements (recurring vs. non-recurring) | Finance |  |  | 2 |  | 0 | 0
Decision on credit cards - who gets, type and threshold | Finance |  |  | 3 |  | 0 | 0
Write-up of formal credit process | Finance |  |  | 3 |  | 0 | 0
Calendarization of standard accounts payable payments/entering | Finance |  |  | 5 |  | 0 | 0
Development of necessary systems including issue tracking | Finance |  |  | 5 |  | 0 | 0
Emergency check approvals, policies | Finance |  |  | 3 |  | 0 | 0
Emergency check form | Finance |  |  | 2 |  | 0 | 0
Inventory/Fixed Asset Management
Development of asset management system (program to use, building it) | Operations / Finance |  |  | 3 |  | 0 | 0
Policies on lost/stolen items (ex textbooks - do students pay) | Operations / Finance |  |  | 4 |  | 0 | 0
Tagging of items (including grantor owned items) | Operations / Finance |  |  | 3 |  | 0 | 0
Initial count of items | Operations / Finance |  |  | 2 |  | 0 | 0
Ongoing inventory counts (how often, process) | Operations / Finance |  |  | 4 | Continuous | 0 | 0
Reconciliation of inventory with the accounting ledger | Operations / Finance |  |  | 4 |  | 0 | 0
Employee Reimbursements
Write-up of official policy | Finance |  |  | 3 |  | 0 | 0
Development of reimbursement form | Finance |  |  | 3 |  | 0 | 0
Training of staff on how to use | Finance |  |  | 3 |  | 0 | 0
Reporting
Revisit timing and what goes to the Board | Finance |  |  | 4 |  | 0 | 0
Design of standard profit & loss format | Finance |  |  | 4 |  | 0 | 0
Design of standard balance sheet format | Finance |  |  | 4 |  | 0 | 0
Design of standard cash flow format | Finance |  |  | 4 |  | 0 | 0
Design of summary commentary | Finance |  |  | 4 |  | 0 | 0
Design of statutory templates | Finance |  |  | 4 |  | 0 | 0
Budget Management
Revisit who is involved, who has final say, basic protocols and what is tracked (I.e. just P&L, balance sheet too? Cash?) | Finance / Operations |  |  | 4 |  | 0 | 0
Budget template adaption to final chart of accounts | Finance |  |  | 2 |  | 0 | 0
Inclusion of internal reporting pieces into the model | Finance |  |  | 3 |  | 0 | 0
Protocols for updating the forecast | Finance |  |  | 4 |  | 0 | 0
Budget review calendarizing | Finance / Operations |  |  | 4 |  | 0 | 0
Intra-month forecast changes for overages (ex: principal wants to buy $1,500 in textbooks, but only has $1,200 left, can they move money, what approvals are needed) | Finance |  |  | 4 |  | 0 | 0
SOM training on model | Finance |  |  | 2 |  | 0 | 0
Annual budget process (1 year, 5 year, something else) | Finance / Operations |  |  | 5 |  | 0 | 0
Petty Cash
Agreement on basic policies (amount, who has access, restrictions on use, maximum purchases, approvals required, storage) | Finance |  |  | 4 |  | 0 | 0
Write-up of Petty Cash standardized policies | Finance |  |  | 4 |  | 0 | 0
Petty cash form | Finance |  |  | 4 |  | 0 | 0
Training of operations team | Finance |  |  | 3 |  | 0 | 0
Insurance
Determination of needs | Legal |  |  | 2 |  | 0 | 0
Safety plan | Operations |  |  | 3 |  | 0 | 0
Claims process - written protocol | Operations |  |  | 2 |  | 0 | 0
Other potential things to look at:
Food service cash management | Operations / Finance |  |  | 3 |  | 0 | 0
Athletic cash management | Operations / Finance |  |  | 3 |  | 0 | 0

## Grants
TASKS & STEPS | Team Member(s): | Target Date | School #1 Project Status | School #2 Project Status | Evidence of Status | NOTES | Final Completion Date
GRANTS |  |  | Completion (0 = not started, 10 = Complete) | Completion (0 = not started, 10 = Complete)
Erate |  |  | 0 | 0
TANF |  |  | 0 | 0
Title I |  |  | 0 | 0
Title IIA |  |  | 0 | 0
Title IID |  |  | 0 | 0
Title IV |  |  | 0 | 0
Title V |  |  | 0 | 0
PCSP Grant |  |  | 0 | 0
8G |  |  | 0 | 0
Stimulus Funds |  |  | 0 | 0
REAP |  |  | 0 | 0
IDEA |  |  | 0 | 0
ARRA Title I |  |  | 0 | 0
IDEA ARRA |  |  | 0 | 0
Educational Excellence Fund |  |  | 0 | 0
PARENTS/STUDENTS
Title I Compact distributed |  |  | 0 | 0
Title I Binders - all years available |  |  | 0 | 0
COMPETITIVE APPLICATIONS